EXPERIMENT ROADMAP

xOS

Validate Before You Build

Test the riskiest assumptions first. Reduce uncertainty with evidence, not opinions.

Based on David Bland’s Testing Business Ideas framework (Desirability × Viability × Feasibility).

Bjarn Brunenberg

February 2026

CONFIDENTIAL

# 1. xOS Idea Scorecard

Before investing time and money, every business idea should be rigorously evaluated. Using a three-criteria framework weighted by importance, here is how xOS scores as a business opportunity.

## 1.1 Specificity (40% weight) — Score: 7.5/10

Problem clarity: Strong. CRO teams are expensive (€800K–€2M/year for 8–12 specialists), workflows are fragmented across 5+ tools, and knowledge doesn’t compound. The problem is real and quantifiable.

Target audience: Good but needs sharpening. Two distinct segments: (1) mid-market to enterprise companies with 3+ CRO specialists, and (2) individual experimentation practitioners. The B2B segment is clearer and higher-value.

Solution approach: Clear and differentiated. An AI operating system built on Claude Code with specialized skills, MCP integrations, and a marketplace for expert brains. Nobody else is building this specific combination.

## 1.2 Focus (30% weight) — Score: 6.0/10

Core value proposition: “Replace 80% of manual CRO work” is compelling and measurable. Strong.

Scope risk: The vision spans 9 technical modules, a marketplace, a consulting arm, a dashboard, team and individual subscriptions, and GitHub distribution. This is a LOT for v1. The biggest risk is trying to do everything at once and delivering nothing well.

Recommendation: Narrow to ONE beachhead customer and ONE killer module for v1. The rest is roadmap, not launch.

## 1.3 Relevance (30% weight) — Score: 8.5/10

Market timing: Near-perfect. AI agents are mainstream conversation. Claude Code is gaining traction. Companies are asking “how do we use AI for growth?” xOS answers that question specifically for experimentation.

Problem significance: High. The promise of 80% cost reduction while maintaining velocity is exactly what CFOs want to hear.

Competitive landscape: No direct competitor. VWO and Optimizely are testing tools, not operating systems. CRO agencies sell labor, not intelligence. First-mover advantage is real.

Overall Score

| Criterion | Weight | Score | Weighted |
| --- | --- | --- | --- |
| Specificity | 40% | 7.5 | 3.00 |
| Focus | 30% | 6.0 | 1.80 |
| Relevance | 30% | 8.5 | 2.55 |
| TOTAL | 100% |  | 7.35 / 10 |

VERDICT: 7.35/10 Strong idea with high market relevance and clear problem-solution fit. The main risk is scope: the vision is broad enough to become unfocused. Narrow the v1 scope aggressively and this scores 8+.

# 2. Business Model (Updated)

## 2.1 Revenue Streams

| Stream | Price | Description |
| --- | --- | --- |
| Base Subscription (xOS Brain) | €19/month | Core experimentation operating system. Full brain with hypothesis factory, experiment design, analysis engine, report generator. Hosted on private GitHub. Continuous updates, bug fixes, new MCPs. |
| Hero Brain Add-on | €29/month | Choose up to 5 “hero brains” from the marketplace. Access expert brains from Ton Wesseling (statistics), Erin Weigel (design), Lukas Vermeer (strategy), Kevin Anderson (career/benchmarking), and more. |
| Enterprise Implementation | €15–25K one-time | Bjarn implements xOS at the company. Sets up Claude Code, connects tools, trains the 2 human operators. Includes first 5 experiments guided. |
| Enterprise Team License | Custom pricing | Multi-seat license for teams. Volume discounts. Dedicated support. Custom integrations. |

## 2.2 Revenue Distribution

Base subscription revenue goes entirely to xOS (Bjarn). Hero brain revenue is shared: the majority goes to xOS, with a percentage going to the contributing expert. Experts whose brains are used most get a higher percentage as an incentive — creating a virtuous cycle where the best content earns the most.

## 2.3 Two Sales Channels

Channel 1 — Self-Serve Subscriptions: Individual and team plans via private GitHub access. LinkedIn thought leadership as primary acquisition. Community-driven growth.

Channel 2 — Enterprise Implementation: High-touch consulting. Bjarn goes into companies, sets up xOS, trains the team. High-ticket (€15–25K) that also converts to ongoing subscriptions.

# 3. Riskiest Assumptions — D × V × F

Following David Bland’s framework from Testing Business Ideas, every business idea rests on three types of assumptions. Desirability: do customers want this? Viability: can we make money? Feasibility: can we build and deliver it? The riskiest assumptions must be tested first.

## 3.1 Desirability — “Do they want this?”

| ID | Assumption | Risk | Evidence Today | Why It Matters |
| --- | --- | --- | --- | --- |
| D1 | CRO teams actively suffer from fragmented tooling and want a unified operating system | HIGH | Anecdotal from Bjarn’s own experience. No systematic customer evidence. | If teams are “fine” with their current setup, there’s no compelling reason to buy. |
| D2 | Companies will trust an AI system for strategic experimentation decisions | CRITICAL | Zero evidence. Single biggest unknown. | If companies don’t trust AI output, xOS becomes a toy, not a tool. |
| D3 | CRO managers will champion (not block) a tool that replaces 80% of their team’s work | HIGH | No evidence. Turkeys don’t vote for Christmas. | The buyer and user may have conflicting incentives. Head of CRO might see xOS as a threat. |
| D4 | Individual practitioners will pay €19/mo for a pre-built brain vs. building their own | MEDIUM | Evo’s Second Brain sold €50K+ in 2 months. Market proof exists. | If people prefer DIY, the subscription model fails for individuals. |
| D5 | People want to “rent” a thought leader’s brain vs. reading their content/courses | HIGH | No evidence. Completely new concept. | If hero brains don’t feel better than free content + ChatGPT, nobody upgrades to €29. |
| D6 | The addressable market is large enough to sustain the business | MEDIUM | Global A/B testing market ~$1.6B. Thousands at experimentation conferences. | If the market is too niche, revenue caps out quickly. |

## 3.2 Viability — “Can we make money?”

| ID | Assumption | Risk | Evidence Today | Why It Matters |
| --- | --- | --- | --- | --- |
| V1 | €19/month generates enough subscribers for meaningful revenue | MEDIUM | SaaS benchmarks suggest this range works for individual tools. | Too low = leaves money on table. Too high = limits adoption. |
| V2 | €29/month hero tier justifies the 50% price increase | MEDIUM | No evidence. | If hero brains aren’t worth €10 more, upgrade rates near zero. |
| V3 | Thought leaders will build and maintain their brains for a revenue share | HIGH | No commitments yet. Just Bjarn’s idea. | If experts don’t participate, the marketplace doesn’t exist. |
| V4 | Enterprise companies will pay €15–25K for implementation | MEDIUM | Consulting market validates willingness to pay for setup. | If companies learn Claude Code fast, implementation fee is hard to justify. |
| V5 | Monthly churn stays below 5% | HIGH | No evidence. AI tool fatigue is real in 2025-2026. | If people try for a month and churn, the LTV doesn’t support the business. |

## 3.3 Feasibility — “Can we build it?”

| ID | Assumption | Risk | Evidence Today | Why It Matters |
| --- | --- | --- | --- | --- |
| F1 | Claude Code’s skill/MCP architecture reliably supports the full xOS workflow | MEDIUM | Bjarn’s own brain works. Architecture proven at small scale. | If skills conflict or break at scale, the product fails. |
| F2 | Non-technical CRO professionals can install, configure, and use Claude Code daily | CRITICAL | Bjarn’s community has “very low” Claude Code literacy. | If the target user can’t use the tool, nothing else matters. Potential dealbreaker. |
| F3 | The “secret sauce” can be protected when packaged via MCP | HIGH | Mateusz working on MCP packaging. Not yet proven. | If buyers can see/copy the skills, there’s no moat and no recurring revenue. |
| F4 | AI brain produces consistently reliable analysis (not hallucinated stats) | HIGH | LLMs struggle with statistical reasoning. No evidence xOS is different. | If analysis is wrong even 10% of the time, trust collapses. |
| F5 | GitHub-based distribution with subscription access control works at scale | MEDIUM | GitHub private repos with team access is established. | Operational headache if subscription management becomes manual. |

# 4. Prioritized Test Plan

Not all assumptions are equal. Some are critical (if wrong, the entire idea fails). The table below ranks all assumptions by risk and maps each to a specific experiment from David Bland’s Testing Business Ideas.

| # | ID | Assumption | Bucket | Risk | Test Method (Bland) | Timeline |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | D2 | Companies trust AI for experimentation decisions | Desir. | CRITICAL | Customer Interviews (p.106) + Expert Interviews (p.115) | Week 1 |
| 2 | F2 | Non-technical CROs can use Claude Code | Feas. | CRITICAL | Concierge (p.248) — walk 3 users through xOS manually | Week 2–3 |
| 3 | D3 | CRO managers won’t block as job threat | Desir. | HIGH | Customer Interviews (p.106) with CRO managers specifically | Week 1 |
| 4 | D1 | Real pain from fragmented CRO tooling | Desir. | HIGH | Discovery Survey (p.122) + Online Ad (p.146) | Week 1–2 |
| 5 | D5 | People want to rent thought leader brains | Desir. | HIGH | Simple Landing Page (p.260) — measure sign-up intent | Week 2 |
| 6 | V3 | Thought leaders will participate for rev share | Viab. | HIGH | Partner Interviews (p.114) with Ton, Erin, Lukas, Kevin | Week 2 |
| 7 | F4 | AI produces reliable statistical analysis | Feas. | HIGH | Data Sheet (p.190) — test on 10 past experiments | Week 3–4 |
| 8 | V5 | Monthly churn stays below 5% | Viab. | HIGH | Track from day 1. Set up cohort analysis. | Post-launch |
| 9 | F3 | IP protection via MCP works | Feas. | HIGH | Partner Interview with Mateusz (p.114) | Week 2 |
| 10 | D4 | Practitioners pay €19/mo vs. DIY | Desir. | MEDIUM | Presale (p.274) — early access at €19/mo | Week 3 |
| 11 | V1 | €19/mo is the right price point | Viab. | MEDIUM | Online Ad (p.146) — test different price points | Week 2–3 |
| 12 | D6 | Market is large enough | Desir. | MEDIUM | Search Trend Analysis (p.126) + Web Traffic Analysis (p.130) | Week 1 |
| 13 | F1 | Claude Code architecture supports full workflow | Feas. | MEDIUM | Feature Stub (p.156) — build one end-to-end flow | Week 3–4 |
| 14 | V4 | Companies pay €15–25K for implementation | Viab. | MEDIUM | Letter of Intent (p.294) — 2–3 company commitments | Week 4 |

# 5. The 4-Week Pre-MVP Validation Sprint

Before going to Brazil and investing development time, run this 4-week sprint to gather evidence on your riskiest assumptions. Total budget: under €500. If all goes well, you’ll have enough conviction (and early revenue signals) to greenlight development.

## Week 1: Discovery — Talk to People

Goal: Understand if the pain is real and if people trust AI for experimentation.

| Day | Activity | Method (Bland) | Target | Success Metric |
| --- | --- | --- | --- | --- |
| Mon–Tue | 5 Customer Interviews with CRO professionals | Customer Interviews (p.106) | CRO specialists, managers | 4/5 confirm fragmentation pain AND openness to AI |
| Wed | 3 Expert Interviews with CRO leaders | Expert Interviews (p.115) | Senior CROs | 2/3 would consider an AI operating system |
| Thu | Market sizing analysis | Search Trend + Web Traffic Analysis | N/A | Addressable market > 10,000 potential users |
| Fri | Synthesize learnings. Go/No-Go on Week 2. | Team decision | N/A | Clear signal on D1, D2, D3 |

## Week 2: Signal Testing — Attract Interest

Goal: Test whether the value proposition resonates and whether partners are interested.

| Day | Activity | Method (Bland) | Target | Success Metric |
| --- | --- | --- | --- | --- |
| Mon | Build xOS landing page (Carrd or similar) with email capture | Simple Landing Page (p.260) | Public | Live page with clear value proposition |
| Tue–Wed | Run LinkedIn + targeted ads (€100–200 budget) | Online Ad (p.146) | CRO professionals | > 5% CTR, > 15% email conversion |
| Thu | Call Ton Wesseling, Erin, Lukas, Kevin about hero brains | Partner Interviews (p.114) | Thought leaders | 2+ express genuine interest in contributing |
| Thu | Call Mateusz about MCP packaging / IP protection | Partner Interview (p.114) | Second Brain Factory | Clear understanding of packaging feasibility |
| Fri | Synthesize. Count sign-ups. Go/No-Go on Week 3. | Team decision | N/A | 50+ email sign-ups, 2+ partner commits |

## Week 3: Validation — Can People Use It?

Goal: Test usability with non-technical CROs and validate willingness to pay.

| Day | Activity | Method (Bland) | Target | Success Metric |
| --- | --- | --- | --- | --- |
| Mon–Tue | Build minimal concierge: one skill (hypothesis factory) | Feature Stub (p.156) | N/A | Working hypothesis-to-output flow |
| Wed–Thu | Walk 3 CRO professionals through using it (screen share) | Concierge (p.248) | 3 non-technical CROs | 2/3 complete flow with minimal hand-holding |
| Thu | Send presale offer to email list at €19/mo early bird | Presale (p.274) | Email list | 5+ presales (10% of list) |
| Fri | Share €29/mo hero tier concept, measure upgrade interest | Landing Page variant | Email list | 30%+ of €19 buyers interested in €29 |

## Week 4: Decision Sprint — Build or Pivot?

Goal: Compile all evidence and make the final go/no-go decision.

| Day | Activity | Details |
| --- | --- | --- |
| Mon–Tue | Test AI quality on 5 real past experiments | Compare xOS analysis output to actual human analyst results. Score accuracy. |
| Wed | Compile evidence dashboard | Single-page evidence summary from all metrics across Weeks 1–3. |
| Thu | Enterprise outreach: 2–3 companies for Letter of Intent | Gauge willingness to pay €15–25K for implementation. |
| Fri | FINAL DECISION: Build / Pivot / Kill | Use Go/No-Go criteria (Section 6). Be honest about the evidence. |

# 6. Go / No-Go Decision Criteria

Use this table at the end of Week 4 to make a rigorous decision. Green = proceed to build. Yellow = adjust and retest. Red = kill or major pivot.

| Metric | Green (Go) | Yellow (Pivot) | Red (Kill) |
| --- | --- | --- | --- |
| Customer interviews confirm pain (D1) | 4/5+ confirm | 3/5 confirm | <3/5 confirm |
| Trust in AI for experimentation (D2) | Openness + curiosity | Skeptical but willing | Strong resistance |
| CRO manager reaction (D3) | See it as empowering | Cautious, not hostile | Active resistance |
| Landing page email conversions | > 15% conversion rate | 8–15% conversion | < 8% conversion |
| Total email sign-ups (€200 spend) | 50+ sign-ups | 25–50 sign-ups | < 25 sign-ups |
| Presale conversions at €19/mo | 5+ paying (10%+) | 2–4 paying | <2 paying |
| Hero brain partner interest | 3+ thought leaders | 1–2 interested | 0 committed |
| Concierge usability test | 2/3 can use it | 1/3 can use it | 0/3 can use it |
| AI analysis quality vs human | 85%+ accuracy | 70–85% accuracy | < 70% accuracy |
| Enterprise interest (LOI) | 2+ companies | 1 company | 0 interested |

REMEMBER You are an experimenter at heart. Eat your own dog food. Run this validation sprint the same way you’d run an experimentation program for a client. Be rigorous. Be honest about the evidence. The goal is not to confirm your excitement — it’s to reduce uncertainty so you can invest with confidence.

# 7. What to Bring to Your Developer in Brazil

If the evidence from Weeks 1–4 gives you a Green or strong Yellow signal, here is what you bring to your developer:

- The Product Vision document (already created)

- This Experiment Roadmap with all evidence collected

- A clear decision on v1 scope: which 2–3 modules to build first (likely: Hypothesis Factory + Analysis Engine + Report Generator)

- Your CLAUDE.md master brain draft — your experimentation philosophy encoded

- A list of MCPs needed: Airtable, VWO, Google Sheets

- Evidence dashboard showing customer demand signals

- 5+ presale customers as proof of demand

- Partner commitments from thought leaders for the marketplace

Test first. Build with evidence. Scale with conviction. This is what xOS teaches companies to do — now do it yourself.